## Executive Risk Dashboard
NexaChain Technologies Ltd — Executive Risk Dashboard ¦ GRC Engagement Q3 2026
OVERALL RISK RATING |  |  |  | FINDINGS SUMMARY |  |  |  |  | COMPLIANCE SCORECARD
CRITICAL |  |  |  | Severity Level |  | Count |  |  | Framework | Score
|  |  |  | Critical |  | 19 |  |  | ISO 27001:2022 | 16%
|  |  |  | High |  | 13 |  |  | NIST CSF 2.0 | 4%
|  |  |  | Medium |  | 1 |  |  | UK GDPR | 12%
|  |  |  | Low |  | 0 |  |  | AI Governance | 0%
TOP 5 CRITICAL FINDINGS — Requiring Immediate Board Action
# | Finding | Why It Matters |  | Recommended Action |  | Risk Owner | Deadline | Status
1 | FraudShield AI freezes customer accounts with NO human review | Illegal under UK GDPR Art.22. Customers wrongly frozen with no appeal. |  | Halt automated freezes immediately. Implement human review gate. |  | CTO — James Wei | Aug 2026 | OPEN
2 | AWS S3 buckets storing 85,000 customer records are UNENCRYPTED | Any attacker accessing S3 gets all customer data in plain text. Immediate GDPR breach. |  | Enable AES-256 encryption on all S3 buckets. Takes hours to implement. |  | IT Manager | Aug 2026 | OPEN
3 | No CISO or DPO appointed. No security leadership at NexaChain. | No one owns security or data protection. Accountability gap at leadership level. |  | Appoint CISO and DPO immediately. Register DPO with ICO. |  | CEO — David Okafor | Aug 2026 | OPEN
4 | No MFA across any NexaChain system. No password policy. | Any compromised password gives full system access. Account takeover risk is critical. |  | Deploy MFA across all systems. Implement password policy. |  | IT Manager | Aug 2026 | OPEN
5 | Former employees retain active system access. No access reviews ever done. | Ex-staff could access crypto wallets, customer data, trading systems at any time. |  | Emergency access audit. Revoke all former employee access immediately. |  | IT Manager | Aug 2026 | OPEN
REMEDIATION TIMELINE — Action Priority by Deadline
Deadline |  |  | Actions Due |  | Priority Level |  | Key Focus Areas
August 2026 |  |  | 19 Critical Actions |  | IMMEDIATE |  | MFA, encryption, access revocation, CISO/DPO appointment, IRP, FraudShield human oversight, DPAs
September 2026 |  |  | 13 High Actions |  | URGENT |  | Security training, EDR deployment, network security, policy updates, privacy notices, AI governance policy
October 2026 |  |  | 1 Medium Action |  | MONITOR |  | Penetration testing commissioning