## Master Findings Log
Finding ID | Source Phase | Category | Severity | Finding Description | Framework Reference | Recommendation | Risk Owner | Target Date | Status
GOV-001 | Phase 3 — Governance | Governance | CRITICAL | No Incident Response Plan exists at NexaChain. There is no structured procedure for detecting, containing, or recovering from a cyberattack or data breach. | ISO 27001 A.5.24 ¦ NIST RS.RP | Develop and implement a formal Incident Response Plan covering detection, containment, eradication, recovery and post-incident review. | CTO — James Wei | Aug 2026 | Open
GOV-002 | Phase 3 — Governance | Governance | CRITICAL | No Risk Register existed prior to this engagement. NexaChain had no visibility of its risks, threats or vulnerabilities. | ISO 27001 A.8.8 ¦ NIST ID.RA | Maintain and regularly update the Risk Register produced in this engagement. Assign risk owners and review quarterly. | CTO — James Wei | Aug 2026 | Open
GOV-003 | Phase 3 — Governance | Governance | CRITICAL | No Chief Information Security Officer (CISO) or dedicated security leadership exists at NexaChain. Information security accountability is not assigned at leadership level. | ISO 27001 A.5.2 ¦ NIST GV.RR-01 | Appoint a qualified CISO or designate a senior leader as accountable for information security immediately. | CEO — David Okafor | Aug 2026 | Open
GOV-004 | Phase 3 — Governance | Governance | CRITICAL | No Data Protection Officer (DPO) has been appointed. Given the volume of personal data NexaChain processes for 85,000 customers, a DPO is likely required under UK GDPR. | UK GDPR Art. 37 ¦ ISO 27001 A.5.2 | Appoint a qualified DPO with sufficient independence and resources. Register DPO details with the ICO. | CEO — David Okafor | Aug 2026 | Open
GOV-005 | Phase 3 — Governance | Governance | CRITICAL | No Business Continuity Plan exists. NexaChain has no documented plan for maintaining operations during a cyberattack, system failure, or other disruption. | ISO 27001 A.5.29 ¦ NIST RC.RP | Develop and implement a Business Continuity Plan covering critical processes, recovery time objectives, and communication procedures. | COO | Aug 2026 | Open
ISO-001 | Phase 5 — ISO 27001 | Information Security | CRITICAL | No MFA confirmed across NexaChain systems. No formal password policy documented. Authentication standards are not defined. | ISO 27001 A.8.5 ¦ NIST PR.AA-03 | Implement MFA across all systems immediately. Establish a formal password policy meeting minimum complexity requirements. | IT Manager — Remi Adeyemi | Aug 2026 | Open
ISO-002 | Phase 5 — ISO 27001 | Access Control | CRITICAL | All developers have admin access to production systems. No privileged access management in place. Former employees may retain active accounts. | ISO 27001 A.8.2 ¦ A.9 ¦ NIST PR.AA-01 | Implement principle of least privilege. Remove unnecessary admin rights. Conduct emergency access review. Deploy Privileged Access Management. | IT Manager — Remi Adeyemi | Aug 2026 | Open
ISO-003 | Phase 5 — ISO 27001 | Data Security | CRITICAL | AWS S3 buckets storing customer PII are confirmed unencrypted. All 85,000 customer records stored in plain text with no encryption protection. | ISO 27001 A.8.24 ¦ UK GDPR Art. 32 ¦ NIST PR.DS-01 | Enable AES-256 encryption on all AWS S3 buckets immediately. Develop a cryptography and key management policy. | IT Manager — Remi Adeyemi | Aug 2026 | Open
ISO-004 | Phase 5 — ISO 27001 | Monitoring | CRITICAL | No SIEM or security monitoring system exists. Security events across NexaChain systems are not captured, retained, or analyzed. | ISO 27001 A.8.15 ¦ A.8.16 ¦ NIST DE.CM-01 | Deploy a SIEM solution to collect and analyze logs from all critical systems. Define log retention policy of minimum 12 months. | IT Manager — Remi Adeyemi | Aug 2026 | Open
ISO-005 | Phase 5 — ISO 27001 | Training | CRITICAL | No security awareness training has ever been conducted at NexaChain. Staff cannot identify phishing emails, social engineering, or security threats. | ISO 27001 A.6.3 ¦ NIST PR.AT-01 | Implement mandatory annual security awareness training for all staff. Include phishing simulation exercises quarterly. | HR | Aug 2026 | Open
ISO-006 | Phase 5 — ISO 27001 | Access Control | CRITICAL | Former employees retain active system access. No offboarding security procedure exists. Access has never been revoked upon termination. | ISO 27001 A.6.5 ¦ NIST PR.AA-01 | Conduct immediate audit of all active user accounts. Revoke access for all former employees. Implement formal offboarding checklist. | IT Manager — Remi Adeyemi | Aug 2026 | Open
ISO-007 | Phase 5 — ISO 27001 | Backup | CRITICAL | No backup policy or recovery test records exist. NexaChain cannot confirm its data can be recovered after an incident or ransomware attack. | ISO 27001 A.8.13 ¦ NIST RC.RP-01 | Implement automated backup solution with offsite copies. Test restoration quarterly. Document backup and recovery procedure. | IT Manager — Remi Adeyemi | Aug 2026 | Open
GDPR-001 | Phase 5 — UK GDPR | Data Protection | CRITICAL | No Records of Processing Activities (ROPA) exists. Required under UK GDPR Article 30 for organizations of NexaChain's size processing 85,000 customer records. | UK GDPR Art. 30 | Create a comprehensive ROPA documenting all personal data processing activities, lawful basis, retention periods, and third parties involved. | DPO | Aug 2026 | Open
GDPR-002 | Phase 5 — UK GDPR | Data Protection | CRITICAL | No Data Processing Agreements exist with third party processors including the NexaBot provider. UK GDPR Article 28 makes DPAs mandatory. | UK GDPR Art. 28 | Immediately establish Data Processing Agreements with all third party processors handling customer personal data. | DPO | Aug 2026 | Open
GDPR-003 | Phase 5 — UK GDPR | Data Protection | CRITICAL | No breach notification procedure exists. NexaChain cannot currently meet the 72-hour ICO notification requirement under UK GDPR Article 33. | UK GDPR Art. 33 ¦ Art. 34 | Develop breach notification procedure including 72-hour ICO notification template and customer notification process. | DPO | Aug 2026 | Open
GDPR-004 | Phase 5 — UK GDPR | Data Protection | CRITICAL | No documented process exists for handling Subject Access Requests or any of the 8 individual rights under UK GDPR. ICO inquiry may involve rights requests. | UK GDPR Art. 15-22 | Implement documented procedure for all 8 individual rights. Train compliance team. Set up response tracking. All responses within 1 month. | DPO | Aug 2026 | Open
AI-001 | Phase 6 — AI Governance | AI Governance | CRITICAL | FraudShield AI automatically freezes customer accounts with no human review before or after the freeze is applied. No appeal mechanism exists for affected customers. | UK GDPR Art. 22 ¦ EU AI Act Art. 14 | Immediately implement mandatory human review before any account freeze is applied. Establish a formal customer appeal process. | CTO — James Wei | Aug 2026 | Open
AI-002 | Phase 6 — AI Governance | AI Governance | CRITICAL | No Data Protection Impact Assessment has been conducted for FraudShield or NexaBot. Both systems process customer data in high-risk ways requiring mandatory DPIAs. | UK GDPR Art. 35 | Commission DPIAs for both FraudShield and NexaBot immediately. Engage the DPO once appointed to oversee both assessments. | DPO | Aug 2026 | Open
AI-003 | Phase 6 — AI Governance | AI Governance | CRITICAL | No Data Processing Agreement exists with the NexaBot provider. Customer personal data including full account details is shared with a third party without any contractual data protection obligations. | UK GDPR Art. 28 | Sign a Data Processing Agreement with the NexaBot provider immediately before allowing further data processing. | DPO | Aug 2026 | Open
GOV-006 | Phase 3 — Governance | Governance | HIGH | The Information Security Policy was written in 2022 and has never been updated. It does not cover cloud operations, AI systems, or crypto-specific risks. | ISO 27001 A.5.1 | Conduct a full review and update of the Information Security Policy. Review annually thereafter. | CTO — James Wei | Sep 2026 | Open
GOV-007 | Phase 3 — Governance | Governance | HIGH | No Acceptable Use Policy exists. Staff have no documented guidance on acceptable use of company systems, devices, and data. | ISO 27001 A.5.10 | Develop and implement an Acceptable Use Policy. Communicate to all staff and obtain signed acknowledgment. | HR | Sep 2026 | Open
GOV-008 | Phase 3 — Governance | Governance | HIGH | No formal KYC and AML procedure is documented. The KYC process exists informally but cannot be demonstrated to regulators. | UK MLR 2017 ¦ FATF ¦ FCA Rules | Document the KYC and AML procedure formally. Train all relevant staff. Appoint a Money Laundering Reporting Officer (MLRO). | Head of Compliance — Sarah Mitchell | Sep 2026 | Open
GOV-009 | Phase 3 — Governance | Governance | HIGH | No Data Retention and Deletion Policy exists. Customer data may be held indefinitely beyond its required retention period. | UK GDPR Art. 5 ¦ ISO 27001 A.8.10 | Develop a data retention and deletion policy defining retention periods by data type and implementing automated deletion where possible. | DPO | Sep 2026 | Open
GOV-010 | Phase 3 — Governance | Governance | HIGH | No Supplier Security Policy exists. Vendors and third party providers have never been assessed for security risks. | ISO 27001 A.5.19 ¦ NIST ID.SC | Implement a third party risk management program. Assess all critical vendors and establish contractual security requirements. | Head of Compliance — Sarah Mitchell | Sep 2026 | Open
GOV-011 | Phase 3 — Governance | Governance | HIGH | No CISO exists. IT Manager is managing all security responsibilities single-handedly which is unsustainable and creates single points of failure. | ISO 27001 A.5.3 ¦ NIST GV.RR-02 | Define and document security roles and responsibilities across all departments. Implement a RACI matrix. | CEO — David Okafor | Sep 2026 | Open
ISO-008 | Phase 5 — ISO 27001 | Network Security | HIGH | No WAF deployed. Network segmentation not documented. Production and development environments not formally separated. | ISO 27001 A.8.20 ¦ NIST PR.IR-01 | Implement WAF for web applications. Document network architecture. Separate production and development environments. | IT Manager — Remi Adeyemi | Sep 2026 | Open
ISO-009 | Phase 5 — ISO 27001 | Endpoint Security | HIGH | Only basic Windows Defender installed on all laptops. No EDR solution. No endpoint encryption. Inadequate for a crypto exchange. | ISO 27001 A.8.1 ¦ A.8.7 ¦ NIST PR.PS | Deploy enterprise-grade EDR solution across all endpoints. Enforce full disk encryption. Implement Mobile Device Management. | IT Manager — Remi Adeyemi | Sep 2026 | Open
ISO-010 | Phase 5 — ISO 27001 | Development | HIGH | No Secure Development Lifecycle policy exists. Custom trading platform built without documented security requirements or code review process. | ISO 27001 A.8.25 ¦ A.8.28 ¦ NIST PR.PS | Implement SDLC policy requiring security at design stage, code reviews, and security testing before deployment. Train developers on OWASP Top 10. | CTO — James Wei | Sep 2026 | Open
GDPR-005 | Phase 5 — UK GDPR | Data Protection | HIGH | Privacy notices may not cover all processing activities including NexaBot AI chatbot data processing and AI-based fraud detection. | UK GDPR Art. 12-14 | Review and update privacy notices to cover all processing activities. Ensure plain English and easy accessibility. | DPO | Sep 2026 | Open
AI-004 | Phase 6 — AI Governance | AI Governance | HIGH | No AI Governance Policy exists at NexaChain. Both AI systems were deployed without any formal governance framework, risk assessment, or executive oversight. | ISO 42001 ¦ NIST AI RMF ¦ EU AI Act Art. 9 | Develop and implement a formal AI Governance Policy covering AI procurement, deployment, monitoring, human oversight, and incident response. | CEO — David Okafor | Sep 2026 | Open
AI-005 | Phase 6 — AI Governance | AI Governance | HIGH | NexaBot has unrestricted access to full customer account data. UK GDPR data minimisation principle requires only necessary data to be accessible. | UK GDPR Art. 5(1)(c) ¦ ISO 27001 A.8.3 | Restrict NexaBot data access to only the minimum customer data fields necessary to answer specific query types. | CTO — James Wei | Sep 2026 | Open
GOV-012 | Phase 3 — Governance | Governance | MEDIUM | No formal penetration testing has ever been conducted. NexaChain has no visibility of its technical vulnerabilities. | ISO 27001 A.8.8 ¦ NIST ID.RA-01 | Commission an immediate penetration test from an accredited provider. Implement quarterly vulnerability scanning thereafter. | CTO — James Wei | Oct 2026 | Open

## Corrective Action Plan
Finding ID | Action Required | Responsible Owner | Target Date | Resources / Support Needed | Current Status | Evidence of Completion
GOV-001 | Develop and implement a formal Incident Response Plan. The plan must cover detection, containment, eradication, recovery and post-incident review. Test the plan with a tabletop exercise within 60 days of completion. | CTO — James Wei | Aug 2026 | External GRC consultant support recommended. Template available in GRC toolkit. | Open | Completed IRP document, tabletop exercise record, staff briefing confirmation
GOV-002 | Maintain and update the Risk Register produced in this engagement. Assign named risk owners for every risk. Schedule quarterly risk review meetings. | CTO — James Wei | Aug 2026 | Risk Register already produced in Phase 4 of this engagement. | Open | Updated Risk Register, quarterly review meeting minutes
GOV-003 | Appoint a qualified CISO. Define the role, responsibilities, and reporting line. Advertise immediately or appoint an interim CISO from existing senior staff. | CEO — David Okafor | Aug 2026 | Recruitment budget required. Interim option: appoint CTO as acting CISO until permanent hire. | Open | CISO appointment letter, updated org chart, role definition document
GOV-004 | Appoint a qualified Data Protection Officer with sufficient independence. Register DPO details with the ICO immediately upon appointment. | CEO — David Okafor | Aug 2026 | Recruitment budget or outsourced DPO service required. Estimated cost £500-£2,000 per month for outsourced DPO. | Open | DPO appointment letter, ICO registration confirmation
GOV-005 | Develop a Business Continuity Plan identifying critical processes, recovery time objectives, and communication procedures. Test annually. | COO | Aug 2026 | BCP template available. Workshop with department heads required to identify critical processes. | Open | Completed BCP document, BCP test record
ISO-001 | Deploy MFA across all NexaChain systems and applications immediately. Develop and communicate a formal password policy. | IT Manager — Remi Adeyemi | Aug 2026 | MFA solution — Microsoft Authenticator or similar. Estimated implementation 2-5 days. | Open | MFA deployment confirmation, password policy document, staff communication record
ISO-002 | Conduct immediate audit of all active user accounts. Remove admin rights from all developers. Revoke access for all former employees. Implement quarterly access reviews going forward. | IT Manager — Remi Adeyemi | Aug 2026 | IT Manager to lead. Head of HR to provide complete list of current and former employees. | Open | Access audit report, account removal records, quarterly review schedule
ISO-003 | Enable AES-256 encryption on all AWS S3 buckets immediately. This is a configuration change that can be completed within hours. Develop encryption and key management policy. | IT Manager — Remi Adeyemi | Aug 2026 | AWS console access required. No additional cost — encryption is built into AWS S3. | Open | AWS encryption configuration screenshot, encryption policy document
ISO-004 | Deploy a SIEM solution to collect and analyze security logs from all critical systems. Define alerting rules and monitoring procedures. | IT Manager — Remi Adeyemi | Aug 2026 | SIEM solution required — Microsoft Sentinel, Splunk, or equivalent. Budget approval needed. | Open | SIEM deployment confirmation, monitoring dashboard screenshot, alerting rules document
ISO-005 | Implement mandatory security awareness training for all 47 staff immediately. Include phishing simulation exercise within 30 days of training. | HR | Aug 2026 | Training platform required — KnowBe4, Proofpoint, or equivalent. Estimated cost £500-£2,000 per year. | Open | Training completion records showing 100% staff completion, phishing simulation results
ISO-006 | Conduct emergency audit of all active user accounts against current employee list. Revoke all access for former employees immediately. Implement formal offboarding checklist. | IT Manager — Remi Adeyemi | Aug 2026 | HR to provide complete list of all current and former employees with dates of departure. | Open | Access audit report, account revocation records, offboarding checklist document
ISO-007 | Implement automated daily backup solution with encrypted offsite copies. Test restoration within 30 days of implementation. | IT Manager — Remi Adeyemi | Aug 2026 | Cloud backup solution — AWS Backup or equivalent. Estimated cost £200-£500 per month. | Open | Backup configuration evidence, successful restoration test record
GDPR-001 | Create comprehensive Records of Processing Activities documenting all 85,000 customer personal data processing activities including purpose, lawful basis, data categories, retention periods and third parties. | DPO | Aug 2026 | DPO to lead once appointed. Data mapping exercise required across all departments. | Open | Completed ROPA document signed by DPO
GDPR-002 | Sign Data Processing Agreements with all third party processors. Priority: NexaBot provider, AWS, FraudShield provider. | DPO | Aug 2026 | Legal counsel support recommended for DPA drafting. ICO provides DPA template guidance. | Open | Signed DPA copies for all third party processors
GDPR-003 | Develop breach notification procedure covering 72-hour ICO notification and customer notification process. Create notification templates. Brief Head of Compliance. | DPO | Aug 2026 | ICO breach notification guidance available at ico.org.uk. | Open | Breach notification procedure document, ICO notification template, customer notification template
GDPR-004 | Implement documented procedure for all 8 individual rights including SAR response process. Train compliance team. Set up response tracking system. | DPO | Aug 2026 | ICO guidance on individual rights available at ico.org.uk. Response tracking can be managed in Excel initially. | Open | Rights procedure document, staff training records, response tracking system evidence
AI-001 | Immediately halt automatic account freezes without human review. Implement a mandatory human review gate for all FraudShield freeze decisions. Establish customer appeal mechanism. | CTO — James Wei | Aug 2026 | Process change only — no additional budget required. CTO to redesign FraudShield workflow with provider. | Open | Updated FraudShield workflow documentation, human review procedure, appeal process document
AI-002 | Commission DPIAs for both FraudShield and NexaBot. DPO to oversee both assessments once appointed. Submit to ICO if high residual risks cannot be mitigated. | DPO | Aug 2026 | ICO DPIA template available at ico.org.uk. External privacy consultant support recommended. | Open | Completed DPIA documents for FraudShield and NexaBot, DPO sign-off
AI-003 | Sign Data Processing Agreement with NexaBot provider immediately before allowing further customer data processing. | DPO | Aug 2026 | Legal counsel support recommended. ICO provides DPA template guidance at ico.org.uk. | Open | Signed DPA with NexaBot provider
GOV-006 | Conduct full review and update of the 2022 Information Security Policy. Include cloud operations, AI systems, crypto risks, and all applicable frameworks. Communicate to all staff. | CTO — James Wei | Sep 2026 | GRC Analyst to support policy update. CISO to approve once appointed. | Open | Updated policy document, staff communication record, acknowledgment log
GOV-007 | Develop and implement an Acceptable Use Policy covering system use, internet, email, social media, BYOD, and data handling. Obtain signed acknowledgment from all staff. | HR | Sep 2026 | GRC Analyst to draft. Legal review recommended. | Open | AUP document, signed acknowledgment records for all 47 staff
GOV-008 | Document KYC and AML procedure formally. Appoint Money Laundering Reporting Officer. Train all relevant staff. Submit to FCA on request. | Head of Compliance — Sarah Mitchell | Sep 2026 | External AML consultant support recommended given FCA registration. | Open | Formal KYC/AML procedure document, MLRO appointment, staff training records
GOV-009 | Develop data retention and deletion policy defining retention periods by data type. Implement automated deletion where possible. | DPO | Sep 2026 | DPO to lead once appointed. Legal review recommended for retention periods. | Open | Data retention policy document, evidence of deletion procedures in operation
GOV-010 | Implement third party risk management program. Assess all critical vendors including AWS, FraudShield and NexaBot. Establish contractual security requirements. | Head of Compliance — Sarah Mitchell | Sep 2026 | Third party risk questionnaire template available in GRC toolkit. | Open | Third party risk assessments for all critical vendors, updated vendor contracts
GOV-011 | Define and document security roles and responsibilities across all departments. Implement a RACI matrix. Brief all department heads. | CEO — David Okafor | Sep 2026 | RACI template available. CISO to own once appointed. | Open | Security RACI matrix, updated job descriptions, department head briefing records
ISO-008 | Deploy WAF for web applications. Document network architecture. Implement formal network segmentation separating production and development environments. | IT Manager — Remi Adeyemi | Sep 2026 | WAF solution — Cloudflare, AWS WAF, or equivalent. Network diagram tool required. | Open | WAF deployment confirmation, network architecture diagram, segmentation evidence
ISO-009 | Deploy enterprise-grade EDR across all 47 employee endpoints. Enforce full disk encryption on all laptops. Implement Mobile Device Management. | IT Manager — Remi Adeyemi | Sep 2026 | EDR solution — CrowdStrike, SentinelOne, or Microsoft Defender for Business. Budget required. | Open | EDR deployment evidence across all endpoints, encryption confirmation, MDM configuration
ISO-010 | Implement Secure Development Lifecycle policy requiring security requirements at design, code reviews before deployment, and SAST/DAST scanning. Train dev team on OWASP Top 10. | CTO — James Wei | Sep 2026 | SAST/DAST tools — SonarQube, Checkmarx, or equivalent. Developer training budget required. | Open | SDLC policy document, first code review records, developer training completion
GDPR-005 | Review and update privacy notices to cover all processing activities including NexaBot AI chatbot and FraudShield AI automated decisions. Ensure plain English and easy accessibility. | DPO | Sep 2026 | DPO to lead. Legal review recommended. ICO guidance available. | Open | Updated privacy notice, evidence of publication on website and app
AI-004 | Develop and implement a formal AI Governance Policy covering AI procurement, deployment, monitoring, human oversight, and incident response for all AI systems. | CEO — David Okafor | Sep 2026 | GRC Analyst to draft with input from CTO and DPO. Board approval required. | Open | AI Governance Policy document, board approval record
AI-005 | Restrict NexaBot data access to only the minimum customer data fields necessary for each query type. Conduct data mapping exercise to define appropriate access scopes. | CTO — James Wei | Sep 2026 | CTO to work with NexaBot provider to implement API-level data access restrictions. | Open | Updated NexaBot data access configuration, data mapping document